## BOQ - GPS RORA
A | Minor Repair work in GPS Rora - DI KHAN
S/N | Items | Specification | Unit | Quantity | Unit Rate | Total Cost
[5 empty] | PKR | PKR
1 | Brick Work | Pacca brick work ,Cement, sand mortar 1:4 | Cft | 315 |  | 0
2 | Plaster | 1/2" thick cement plaster 1:4 on walls, inner, outer sides, including making edges, corners, and curing, etc., complete in all aspects. | sft | 840 |  | 0
| Total Amount |  |  |  |  | 0

## BOQ- GPS BALI SHOMALI
A | Minor Repair work in GPS Bali shomali - DI KHAN
S/N | Items | Specification | Unit | Quantity | Unit Rate | Total Cost
[5 empty] | PKR | PKR
1 | Cement Sand Mortar 1 : 4 (one Cement: 4 Sand) and brick work | Cement Sand Mortar 1 : 4 (one Cement: 4 Sand) for the construction of boundary wall on existing bricks | Cft | 504 |  | 0
2 | Plaster | 1/2" thick cement plaster 1:4 on walls, inner, outer sides, including making edges, corners, and curing, etc., complete in all aspects. | sft | 1344 |  | 0
| Total A |  |  |  |  | 0

## BOQ - GPS GANDI ASHIQ
A | Repair work
Minor Repair work in GPS GANDI ASHIQ -DI KHAN
S/N | Items | Specification | Unit | Quantity | Unit Rate | Total Cost
[5 empty] | PKR | PKR
7 | Main enterance gate of school (length10.25' x height 9') | Supplying and fixing 18-20 SWG sheet main gate with angle iron (1.5" x 1.5" x 1/8") with locking arrangement, hinges, paint etc. complete (width 10.25 ' Height 9') complete Job | sft | 92.25 |  | 0
| Total A |  |  |  |  | 0

## BOQ - GGPS SHORKOT
A | Minor Repair work in GGPS Shorkot -DI KHAN
S/N | Items | Specification | Unit | Quantity | Unit Rate | Total Cost
[5 empty] | PKR | PKR
4 | Cement Sand Mortar 1 : 4 (one Cement: 4 Sand) and brick work | Cement Sand Mortar 1 : 4 (one Cement: 4 Sand) for the construction of boundary wall on existing bricks | Cft | 338 |  | 0
5 | Plaster | 1/2" thick cement plaster 1:4 on walls, inner, outer sides, including making edges, corners, and curing, etc., complete in all aspects. | sft | 900 |  | 0
| Total A |  |  |  |  | 0

## BOQ -GGPS ZANDAR
A | Minor Repair work in GGPS Zandar - DI KHAN
S/N | Items | Specification | Unit | Quantity | Unit Rate | Total Cost
[5 empty] | PKR | PKR
1 | PCC(1:2:4) | Provide & laying of Plain Cement Concrete 1:2:4, including surface finishing, curing complete finish work | Cft | 12 |  | 0
2 | Brick Work (4' X4') | Pacca brick work ,Cement, sand mortar 1:4 | Cft | 64 |  | 0
3 | Plaster | 1/2" thick cement plaster 1:4 on walls, inner, outer sides, including making edges, corners, and curing, etc., complete in all aspects. | sft | 92 |  | 0
4 | Precast concret Slab | RCC including Precast/Prestressed in slab, beam, column, lintel, girder, etc. (1:1:2) | Cft | 12 |  | 0
5 | DOOR | Supplying and fixing 18-20 SWG sheet door with angle iron (1.5" x 1.5" x 1/8") with locking arrangement, hinges, paint etc. complete (width 3 ' Height 6') complete Job | Sft | 18 |  | 0
5 | Total A |  |  |  |  | 0
Sanitary/plumbing
1 | PPR Pipe | Providing, laying cutting, jointing, PPRC pipeline 1/2" dia in walls/trenches with pipes (confirming to DIN 8077/8078, PN 20 of approved quality for cold/hot water supply systems including the cost of accessories e.g. Socket, Union, Elbow, Tee, Bend, valves etc. Work also includes digging/burying up to 1 feet depth in ground and in walls in all types of soil, soft & hard. | Rft | 80 |  | 0
2 | PVC Pipe | Providing and Fixing 4" dia UPVC pipe including all sanitary fittings from WC to Septick Tank complete as per drawing and specifications | Rft | 30 |  | 0
3 | PVC Pipe | Providing and Fixing 3" dia UPVC pipe including all sanitary fittings for disposal of Latrine waste water complete as per drawing and specifications | Rft | 30 |  | 0
4 | Vent Pipe | Providing and Fixing 2" dia UPVC vent pipe including all specials for instructions of engineer incharge | Rft | 1 |  | 0
5 | Indian WC | Providing and fitting glazed earthen ware water closet (WC), squatter type (Orissa pattern) combined with foot rest, medium size, Complete in all aspects. white in colour Porta, Faisal or Master. | No | 1 |  | 0
6 | Providing and Fixing 'P' trap | Providing and Fixing 'P' trap (Best Quality ceramic) | No | 1 |  | 0
7 | Supply and Fixing of CP floor Truff Jalli with Grating 6"×6" complete | Supply and Fixing of CP floor Truff Jalli with Grating 6"×6" complete | No | 1 |  | 0
8 | Providing and Fixing CP bib-cock, heavy type : 3/4" | Providing and Fixing CP bib-cock, heavy type : 3/4" | No | 1 |  | 0
9 | Water Tank | Supplying and Fixing Polyethylene Water Tank 1000 litres (Horizontal) made from food grade FDA Certified raw material, 3 layers UV stabilized, inert with water, anti-fungus and anti-bacterial and have a service life of more than 10 years. Connection with existing water line including pipe & all fitting (inlet/outlet valves and automatic valve in tank, tee, elbow, union, sockets etc.), proper overflow connection with the drain. Complete in all aspects. | No | 1 |  | 0
| Total B |  |  |  |  | 0
| Total A + Total B |  |  |  |  | 0